## Sheet1
Item No | ID Date | Description | Owner | Due Date | Comments / Resolution | Status
1 | 2023-08-10 | The traffic impact analysis is due back to Gander by the end of September, 2023. | Katie Hamilton | 2023-10-01 |  | Open
2 | 2023-08-10 | Is the lift station and waste water / sewer treatment facility planned or designed to accommodate future inputs. i.e. If we get annexed to Holly Springs in the future is it able to accommodate us. The lift station will be located on the west side of Buckhorn Duncan. | Katie Hamilton | 2023-08-28 | Katie stated in the meeting that she would have answers back to us two weeks from the meeting on the 10th of August. | Open
3 | 2023-08-10 | The waterline will extend all the way from Buckhorn Duncan to Piney Grove - Wilbon. There will be a Fuquay Varina Line and a Holly Springs Line in this plan. Question is if we are able to connect to the line from FV? | Katie Hamilton | 2023-08-28 |  | Open
4 | 2023-08-10 | Since the lot density of the subdivision is severe; 245 units on lots that range from .17 acre (majority) to .27 acre, can you make the lot sizes a minimum of .5 acre to blend into our community and surrounding communities better? | Katie Hamilton | 2023-08-28 |  | Open | 3
5 | 2023-08-10 | Will the proposed subdivision connect to the trailer park now or in the future? | Katie Hamilton | 2023-08-28 |  | Open
6 | 2023-08-10 | Please explain in detail why you are 'required' to connect to our subdivision by the 'Holly Springs Ordinance'. Include the reasoning. You should not connect to us because you are Holly Springs and we are Wake County with a FV address. | Katie Hamilton | 2023-08-28 |  | Open
7 | 2023-08-10 | Although we ae a 'county road', our roads do not meet the county road design specifications. At a minimum if you are running at a minimum of 132 vehicles across our road in the subdivision, you will need to bring the road up to the standard. | Katie Hamilton | 2023-08-28 | This would mean to apply the top coat as a minimum. Other aspects should be looked at by the county or NCDOT engineers. | Open
8 | 2023-08-10 | Gander needs to email everyone in our subdivision and the adjoining subdivisions on all correspondences as this progresses. | Katie Hamilton | 2023-08-28 |  | Open
9 | 2023-08-10 | Since the construction road and subsequent utilities corridor is running from the north phase to the south phase of the development, this is where you should put the connecting road. Do not send that traffic through Duncans Ridge Way. A junior civil engineer can develop the bridging requirements of the creek. | Katie Hamilton | 2023-08-28 | Katie stated that the N-S connecting road "depends on environmental features". We need to understand what that entails and where our benefits may be found. | Open
10 | 2023-08-10 | Bring all of your traffic through our sleepy little community presents a safety issue you will need to address. Besides bringing the road up to standards, sidewalks need to be installed so we can still walk and plan outside and off the now bush thoroughfare. | Katie Hamilton | 2023-08-28 |  | Open
11 | 2023-08-10 | You will need to do a noise mitigation plan to address the noise from your densely populated subdivision affecting the quality of life in our subdivision. | Katie Hamilton | 2023-08-28 |  | Open
12 | 2023-08-10 | How are you addressing the removal of wildlife from your land? We are concerned about the copperheads moving into our neighborhood and the loss of deer. | Katie Hamilton | 2023-08-28 |  | Open
13 | 2023-08-10 | Will you carry liability insurance for copperhead attacks, kids / walkers getting hit by excessive vehicular traffic, and blasting damage? | Katie Hamilton | 2023-08-28 |  | Open
14 | 2023-08-10 | The end of Duncans Ridge Way has unique NPDES runoff concerns. You will need to have a large culvert there or a bridge to jump that area. | Katie Hamilton | 2023-08-28 |  | Open
15 | 2023-08-10 | Besides the storm water runoff into your four runoff ponds, where else does the water run? Any into our subdivision? | Katie Hamilton | 2023-08-28 |  | Open
16 | 2023-08-10 | When will the traffic light be installed on Duncan Cook and Piney Grove? Sooner is better than later. | Katie Hamilton | 2023-08-28 |  | Open
17 | 2023-08-10 | Katie mentioned the "DWR restrictions for roads in their subdivision". Please explain and supply documentation of that regulation. | Katie Hamilton | 2023-08-28 |  | Open
18 | 2023-08-10 | How are you addressing the federally protected bats in the land that you are proposing to disturb? | Katie Hamilton | 2023-08-28 |  | Open
19 | 2023-08-10 | Your recreational amenities are nice (pool, pickle ball court, dog park, playground), however please relocate the pickle ball court to another area. It Is undesirable to be near one of those. With all of those amenities and four water runoff ponds, doesn't leave much land for 246 units. | Katie Hamilton | 2023-08-28 |  | Open
20 | 2023-08-10 | Along with your environmental impact study, please do a human impact for all of the negative results to our community affecting our quality of life and property de-valuations. | Katie Hamilton | 2023-08-28 |  | Open
21 | 2023-08-10 | Please provide the appraiser query results form how our home values are being impacted by your overly dense subdivision going in next to and connecting to us. | Katie Hamilton | 2023-08-28 |  | Open
22 | 2023-08-10 | Will the sewer and water be stubbed at the entrances to Duncans Ridge for future consideration? | Katie Hamilton | 2023-08-28 |  | Open
23 | 2023-08-10 | Is your community going to have natural gas or LP? | Katie Hamilton | 2023-08-28 |  | Open
24 | 2023-08-10 | Please send the results of the geotechnical survey to us with a potential blasting plan. | Katie Hamilton | 2023-08-28 |  | Open
25 | 2023-08-10 | How will your civil work affect the water table and our aquifer that we depend on for our water? | Katie Hamilton | 2023-08-28 |  | Open
26 | 2023-08-10 | How will the additional chemicals added to the water tables in our area from your residential lawn fertilizers going to affect us? | Katie Hamilton | 2023-08-28 |  | Open
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236